FSCA INSPECTION READINESS REPORT

Onsite inspection: 22 September 2026 | Kanaan Trust, FSP 528

| Assessment date | 20 September 2026 |
| --- | --- |
| Inspection scope | BRA; RMCP; section 42A governance; FIC Act training; operating effectiveness |
| Evidence reviewed | FSCA notice, signed-final submission set, KCAS live records and controlled exception registers |
| Overall position | Substantially prepared, but not yet fully audit-ready |

# Executive Conclusion

Kanaan has a strong inspection foundation. The requested documents were submitted, the signed BRA and RMCP are active and Board-approved, governance roles are recorded, the 2026 training evidence is complete, and KCAS provides practical client-level evidence rather than policy statements alone.

Qualified conclusion: Kanaan should not yet describe itself as fully ready. The goAML daily-check record, eight pending operating-evidence tests, and the treatment of positive-value internal/owner records require attention before the inspection.

# Readiness Position

| Area | Position | Evidence / concern |
| --- | --- | --- |
| BRA and RMCP | Ready | Signed and Board-approved on 31 July 2026; active in KCAS with next review dates of 31 July 2027. |
| Governance | Ready | Andre Delport is Board Chair; Gert Delport is MLCO and section 42A responsible person; Andries van Tonder is Internal Compliance Officer and primary goAML user. |
| Training | Ready | Six relevant staff members attended the 2026 FIC Act/RMCP training, signed the register and scored 15/15. |
| Submitted documents | Ready | All FSCA notice items 5.1 to 5.8 are registered as Ready in KCAS and linked to the signed submission evidence. |
| Client assessments | Substantially ready | 164 of 179 positive-value client records are Finalised or Approved. All 164 contain verified PEP/PIP, TFS and adverse-information screening. |
| External exceptions | Controlled but open | Six positive-value records remain open: KIDs 003, 024, 079, 194, 232 and 333. Each has a documented evidence or provider-resolution requirement. |
| Internal/owner records | Decision required | Nine positive-value Finplan, Delport and An-Mar records remain unassessed. They require assessment or a documented determination of their actual non-client/internal status. |
| goAML checks | Not ready | Only five checks are recorded since 31 July 2026; one was Unavailable and four recorded no new messages. This does not evidence the every-business-day control stated in the RMCP. |
| Operating tests | Not ready | Eight KCAS inspection-readiness checks remain Pending: permissions, audit log, sensitive data, backup, restore, rollback, performance and training support. |
| Practical demonstration | Rehearsal required | The live-server demonstration should be tested from an office workstation before the inspectors arrive. |

# Client-Assessment Position

The portfolio-wide compliance-review exercise has covered the clients with positive investment values, but coverage must not be described as universal finalisation. The accurate position at 20 September 2026 is:

179 client records have positive current valuation values in KCAS.

164 are Finalised or Approved.

All 164 finalised positive-value records contain verified PEP/PIP, sanctions/TFS and adverse-information reviews. KCAS contains 893 screening records performed by Codex between 27 July and 20 September 2026.

Six external positive-value records remain controlled exceptions: KIDs 003, 024, 079, 194, 232 and 333.

Nine Finplan, Delport or An-Mar records remain unassessed. Ownership of Kanaan does not itself exempt a genuine client relationship from CDD and client-risk assessment.

The unresolved-client email and the registers under docs/outdated-kyc and docs/unresolved-investments provide the specific remediation required for the six external exceptions.

# Immediate Actions Before 22 September

Perform and record the goAML message-board check on 20 September, 21 September and before the inspection on 22 September. Do not backdate missing checks.

Record the historical goAML frequency gap as a control deficiency, assign remediation, and obtain MLCO acknowledgement. The explanation should be factual and should not suggest that unrecorded checks occurred.

Complete the eight KCAS inspection-readiness checks with dated evidence. Prioritise access permissions, audit trails, opening client evidence, backup/restore evidence and retrieval of training records.

Resolve the nine internal/owner records by assessing genuine client relationships or recording a defensible determination that a record is an internal/non-client accounting record. Retain the basis for that determination.

Keep the six genuine client exceptions open and present the controlled exception registers. Do not create assumed surrender dates or represent missing KYC documents as available.

Conduct a live demonstration rehearsal with Andre, Gert and Andries from an office workstation. Confirm that each person can explain their role and retrieve the evidence relevant to it.

# Recommended Demonstration Sequence

Open the active BRA and explain the Low residual-risk conclusion, the inherent risks and the controls that reduce them.

Open the active RMCP and show Board approval, annual review date, governance ownership and linked controls.

Demonstrate one ordinary natural-person assessment and one trust assessment with ownership/control parties.

Show the screening date and time, sources searched, subject, result, reviewer and audit trail.

Show the unresolved-client and investment registers and explain the specific remediation for an open exception.

Retrieve the signed governance, training, monitoring and approval documents directly from KCAS.

Explain unusual-activity escalation, confidentiality, report timing, goAML responsibilities and the current remediation of the daily-check record.

# Key Personnel

The FSCA notice requires Board/senior-management personnel and the section 42A responsible person to be available. The minimum practical attendance is:

Andre Delport - Board Chair, Trustee and Key Individual.

Gert Delport - CEO, Trustee, MLCO and section 42A responsible person.

Andries van Tonder - Internal Compliance Officer, Trustee and primary goAML user.

# Recommended Wording to FSCA

“We completed the portfolio-wide compliance review of clients with positive investment values. KCAS currently contains 164 finalised or approved positive-value assessments, all with recorded PEP/PIP, TFS and adverse-information screening. Six external client records remain controlled exceptions awaiting identified KYC or provider evidence. Separate internal and owner-related records are being treated according to their actual legal and client status.”

# Evidence Basis

FSCA Notice of Onsite Inspection dated 20 July 2026, including information-document requirements 5.1 to 5.8.

Signed-final submission folder: Business and Governance Factual Confirmation; organogram; 2026 BRA; 2026 and 2025 RMCPs; 2023-2026 training evidence; internal/external audit position letters; monitoring dashboard.

KCAS live records reviewed on 20 September 2026: controlled documents, BRA, RMCP, governance roles, client assessments, screening records, goAML checks, inspection case and readiness checks.

FIC Guidance Note 7A publication: https://www.fic.gov.za/wp-content/uploads/2025/02/2025.2-WN-Guidance-note-7a.pdf

FIC goAML daily-message-board notice dated 25 August 2025: https://www.fic.gov.za/wp-content/uploads/2025/08/Notice-Accountable-institutions-to-visit-goAML-message-board-daily.pdf

FSCA supervisory information: https://www.fsca.co.za/Supervisory-Information/

This document is an internal readiness assessment. It should be updated if additional checks, client assessments or remediation evidence are completed before the inspection.